## Hoja1
TSPi Schedule Planning Template - Form SCHEDULE
Name |  | Rafael Ortega |  |  |  |  | Date |  | 2014-04-23
Team |  | Click IT |  |  |  |  | Instructor |  | Luis Daniel Benavides
Part/Level |  | 1 |  |  |  |  | Cycle |  | 2
|  |  | Plan |  |  | Actual
Week No | Date |  | Direct Hours | Cumulative Hours | Cumulative Planned Value | Hours |  | Cumulative Hours | Week Earned Value | Cumulative Earned Value
6 | 16/04/214 |  | 1.3 | 1.3 | 4.4 | 0 |  | 0 | 0 | 0
7 | 2014-04-23 |  | 7 | 8.3 | 23.9 | 10.5 |  | 10.5 | 28.2 | 28.2
8 | 2014-04-30 |  | 12.5 | 20.8 | 42.7 | 16.3 |  | 26.8 | 42.5 | 70.7
9 | 2014-05-07 |  | 8.5 | 29.3 | 29
|  |  | 29.3 |  | 100