## Hoja1
TSPi Example Task Planning Template - Form TASK
Name |  |  |  | Date | 2014-03-21
Team | Click IT |  |  | Instructor | Luis Daniel Benavides
Part/Level |  |  |  | Cycle | 1
Task |  |  |  | Plan Hours | [6 empty] | Plan Size/Value |  |  |  |  | Actual
Phase | Part | Task Name | # Engineers | Team Leader | Development Manager | Planning Manager | Qual./Proc. Manager | Support Manager | Total Team Hours | Cumulative hours | Size Units | Size | Week No. | Planned Value | Cumulative PV | Hours | Cumulative Hours | Week No.
LAU1 |  | Definir Objetivos | 5 | 2 | 2 | 2 | 2 | 2 | 10 | 10 | Page | 2 | 1 | 6.4 | 6.4 | 9 | 9 | 1
|  | Diligenciar Info Form | 5 | 1 | 1 | 1 | 1 | 1 | 5 | 15 | Page | 5 | 1 | 3.2 | 9.6 | 6 | 15 | 1
|  | Asignar roles | 5 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 1.25 | 16.25 | Page | 1 | 1 | 0.8 | 10.4 | 1 | 16 | 1
STRAT1 |  | Establecer Estrategia | 5 | 1 | 1 | 1 | 1 | 1 | 5 | 21.25 | Page | 1 | 3 | 3.2 | 13.6 | 7 | 23 | 3
|  | Realizar diseño Conceptual | 5 | 0.5 | 2 | 2 | 0.5 | 0.5 | 5.5 | 26.75 | Page | 1 | 3 | 3.5 | 17.1 | 4 | 27 | 3
|  | Generar acta de reunión de documentación de estrategia y criterios | 1 | 0 | 0 | 0 | 0.8 | 0 | 0.8 | 27.55 | Page | 2 | 3 | 0.5 | 17.6
PLAN1 |  | Realizar plan de desarrollo | 5 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 3 | 30.55 | Page | 1 | 3 | 1.9 | 19.5
|  | Realizar estimaciones preliminares de tamaño y tiempo para la estrategia | 2 | 0 | 0.5 | 1 | 0 | 0 | 1.5 | 32.05 | Page | 0.5 | 3 | 1 | 20.5 | 2
|  | Definir la configuracion control process | 5 | 0.3 | 0.3 | 0.3 | 0.3 | 1.5 | 2.7 | 34.75 | Page | 1 | 3 | 1.7 | 22.2
|  | Generar listado de tareas de la semana | 5 | 0.5 | 0.5 | 1 | 0.5 | 0.5 | 3 | 37.75 | Page | 1 | 3 | 1.9 | 24.1
|  | Realizar plan de calidad(Definir estándares) | 5 | 0.3 | 0.3 | 0.3 | 1.5 | 0.3 | 2.7 | 40.45 | Page | 3 | 3 | 1.7 | 25.8
|  | Generar los riesgos del proyecto | 1 | 2 | 0.2 | 0.2 | 0.2 | 0.2 | 2.8 | 43.25 | Page | 2 | 3 | 1.8 | 27.6
|  | Management and miscellaneous(reuniones) | 5 | 3 | 3 | 3 | 3 | 3 | 15 | 58.25 | Page | 5 |  | 9.7 | 37.3
REQ1 |  | Requerimientos funcionales | 2 | 2 | 2 | 2 | 0 | 0 | 6 | 64.25 | Page | 1 |  | 3.9 | 41.2
|  | Interfaz de usuario | 1 | 1 | 1 | 0 | 0 | 1 | 3 | 67.25 | Page | 2 |  | 1.9 | 43.1
|  | Requerimientos de calidad | 1 | 0 | 0 | 0 | 2 | 2 | 4 | 71.25 | Page | 1 |  | 2.6 | 45.7
|  | Restricciones | 1 | 0 | 0 | 0 | 1 | 1 | 2 | 73.25 | Page | 1 |  | 1.3 | 47
DES1 |  | Plan de pruebas de sistema | 2 | 1 | 0 | 1 | 1 | 0 | 3 | 76.25 | Page | 3 |  | 1.9 | 48.9
|  | Diseño de alto nivel | 1 | 0 | 2 | 1 | 0 | 0 | 3 | 79.25 | Page | 2 |  | 1.9 | 50.8
|  | Plan de pruebas de integración | 2 | 1 | 0 | 0 | 0 | 0 | 1 | 80.25 | Page | 1 |  | 0.6 | 51.4
|  | Inspección de diseño de alto nivel | 1 | 2 | 0 | 0 | 1 | 0 | 3 | 83.25 | Page | 0.7 |  | 1.9 | 53.3
|  | Inspección de requerimientos | 1 | 2 | 0.5 | 2 | 0.5 | 0.5 | 5.5 | 88.75 | Page | 0.7 |  | 3.5 | 56.8
IMP1 |  | Planeación de implementación | 2 | 1 | 1 | 0 | 0 | 1 | 3 | 91.75 | Page | 1 |  | 1.9 | 58.7
|  | Diseño detallado | 1 | 0.5 | 0 | 2 | 0 | 0 | 2.5 | 94.25 | Page | 3 |  | 1.6 | 60.3
|  | Revisión de diseño detallado | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 95.25 |  |  |  | 0.6 | 60.9
|  | Desarrollo de pruebas | 1 | 0 | 0 | 1 | 0 | 1 | 2 | 97.25 | Page |  |  | 1.3 | 62.2
|  | Inspección detallada del diseño | 2 | 0 | 0 | 0.5 | 1 | 1 | 2.5 | 99.75 | Page | 0.7 |  | 1.6 | 63.8
|  | Código | 5 | 5 | 5 | 5 | 5 | 5 | 25 | 124.75 | LOC | 646 |  | 16.1 | 79.9
|  | Revisión de código | 5 | 1 | 1 | 0 | 1 | 0 | 3 | 127.75 |  |  |  | 1.9 | 81.8
|  | Inspección de código | 1 | 0 | 0.5 | 0 | 1 | 0.5 | 2 | 129.75 | Page | 0.7 |  | 1.3 | 83.1
TEST1 |  | Pruebas unitarias | 1 | 1 | 1 | 1 | 1 | 1 | 5 | 134.75 | Page | 6 |  | 3.2 | 86.3
|  | Construir e integrar el sistema | 5 | 0 | 1 | 0 | 1 | 1 | 3 | 137.75 |  |  |  | 1.9 | 88.2
|  | Pruebas del sistema | 2 | 0 | 1 | 0 | 2 | 2 | 5 | 142.75 | Page | 10 |  | 3.2 | 91.4
PM1 |  | Documentación | 5 | 1 | 1 | 1 | 1 | 1 | 5 | 147.75 | Page | 5 |  | 3.2 | 94.6
|  | Postmortem | 5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 7.5 | 155.25 | Page | 5 |  | 4.8 | 99.4
|  |  |  | 31.35 | 30.55 | 31.55 | 31.55 | 30.25 | 155.25 |  |  |  |  | 99.4