## Hoja1
TSPi Schedule Planning Template - Form SCHEDULE
Name |  | Fabián Eduardo Becerra Pérez |  |  |  |  | Date |  | 2014-03-21
Team |  | Click IT |  |  |  |  | Instructor |  | Luis Daniel Benavides
Part/Level | [6 empty] | Cycle |  | 1
|  |  | Plan |  |  | Actual
Week No | Date |  | Direct Hours | Cumulative Hours | Cumulative Planned Value | Team Hours |  | Cumulative Hours | Week Earned Value | Cumulative Earned Value
1 | 12/03/214 |  | 3.5 | 3.5 | 11.6 | 3.5 |  | 3.5 | 11.6 | 11.6
2 | 2014-03-19 |  | 0 | 3.5 | 11.6 | 0 |  | 3.5 | 0 | 11.6
3 | 2014-03-26 |  | 9.2 | 12.7 | 42.1 | 8.6 |  | 12.1 | 30.5 | 42.1
4 | 2014-04-02 |  | 4 | 16.7 | 55.4 | 6.5 |  | 18.6 | 11.6 | 53.7
5 | 2014-04-09 |  | 11 | 27.7 | 91.9 | 14.5 |  | 33.1 | 34.9 | 88.6
6 | 2014-04-16 |  | 2.5 | 30.2 | 100 | 6.5 |  | 39.6 | 11.6 | 100.2