## Hoja1
TSPi Schedule Planning Template - Form SCHEDULE
Name |  | Fabián Eduardo Becerra Pérez |  |  |  |  | Date |  | 2014-03-21
Team |  | Click IT |  |  |  |  | Instructor |  | Luis Daniel Benavides
Part/Level | [6 empty] | Cycle |  | 1
|  |  | Plan |  |  | Actual
Week No | Date |  | Direct Hours | Cumulative Hours | Cumulative Planned Value | Team Hours |  | Cumulative Hours | Week Earned Value | Cumulative Earned Value
1 | 12/03/214 |  | 20 | 20 | 11.7 | 16 |  | 16 | 11.7 | 11.7
2 | 2014-03-19 |  | 0 | 20 | 11.7 | 0 |  | 16 | 0 | 11.7
3 | 2014-03-26 |  | 30 | 50 | 28.8
4 | 2014-04-02 |  | 30 | 80 | 52.4
5 | 2014-02-09 |  | 35 | 115 | 64.4
6 | 2014-02-16 |  | 35 | 150 | 100