## Hoja1
TSPi Example Task Planning Template - Form TASK
Name |  |  |  | Date | 2014-03-21
Team | Click IT |  |  | Instructor | Luis Daniel Benavides
Part/Level |  |  |  | Cycle | 1
Task |  |  |  | Plan Hours | [6 empty] | Plan Size/Value |  |  |  |  | Actual
Phase | Part | Task Name | # Engineers | Team Leader | Development Manager | Planning Manager | Qual./Proc. Manager | Support Manager | Total Team Hours | Cumulative hours | Size Units | Size | Week No. | Planned Value | Cumulative PV | Hours | Cumulative Hours | Week No.
LAU1 |  | Definir Objetivos | 5 | 2 | 2 | 2 | 2 | 2 | 10 | 10 | Page | 2 | 1 | 6.7 | 6.7 | 9 | 9 | 1
|  | Diligenciar Info Form | 5 | 1 | 1 | 1 | 1 | 1 | 5 | 15 | Page | 5 | 1 | 3.3 | 10 | 6 | 15 | 1
|  | Asignar roles | 5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 2.5 | 17.5 | Page | 1 | 1 | 1.7 | 11.7 | 1 | 16 | 1
STRAT1 |  | Establecer Estrategia | 5 | 1 | 1 | 1 | 1 | 1 | 5 | 22.5 | Page | 1 | 3 | 3.3 | 15 | 7 | 23 | 3
|  | Realizar diseño Conceptual | 5 | 0.5 | 2 | 2 | 0.5 | 0.5 | 5.5 | 28 | Page | 1 | 3 | 3.7 | 18.7 | 4 | 27 | 3
|  | Generar acta de reunión de documentación de estrategia y criterios | 1 | 0 | 0 | 0 | 0.7 | 0 | 0.7 | 28.7 | Page | 2 | 3 | 0.5 | 19.2
PLAN1 |  | Realizar plan de desarrollo | 5 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 3 | 31.7 | Page | 1 | 3 | 2 | 21.2
|  | Realizar estimaciones preliminares de tamaño y tiempo para la estrategia | 2 | 0 | 0.5 | 1 | 0 | 0 | 1.5 | 33.2 | Page | 0.5 | 3 | 1 | 22.2 | 2
|  | Definir la configuracion control process | 5 | 0.2 | 0.2 | 0.2 | 0.2 | 1.5 | 2.3 | 35.5 | Page | 1 | 3 | 1.5 | 23.7
|  | Generar listado de tareas de la semana | 5 | 0.5 | 0.5 | 1 | 0.5 | 0.5 | 3 | 38.5 | Page | 1 | 3 | 2 | 25.7
|  | Realizar plan de calidad(Definir estándares) | 5 | 0.2 | 0.2 | 0.2 | 1 | 0.2 | 1.8 | 40.3 | Page | 3 | 3 | 1.2 | 26.9
|  | Generar los riesgos del proyecto | 1 | 2 | 0.2 | 0.2 | 0.2 | 0.2 | 2.8 | 43.1 | Page | 2 | 3 | 1.9 | 28.8
|  | Management and miscellaneous(reuniones) | 5 | 3 | 3 | 3 | 3 | 3 | 15 | 58.1 | Page | 5 |  | 10 | 38.8
REQ1 |  | Requerimientos funcionales | 2 | 2 | 2 | 2 | 0 | 0 | 6 | 64.1 | Page | 1 |  | 4 | 42.8
|  | Interfaz de usuario | 1 | 1 | 1 | 0 | 0 | 1 | 3 | 67.1 | Page | 2 |  | 2 | 44.8
|  | Requerimientos de calidad | 1 | 0 | 0 | 0 | 2 | 1 | 3 | 70.1 | Page | 1 |  | 2 | 46.8
|  | Restricciones | 2 | 0 | 0 | 0 | 0.5 | 1.5 | 2 | 72.1 | Page | 1 |  | 1.3 | 48.1
DES1 |  | Plan de pruebas de sistema | 2 | 1 | 0 | 0 | 1 | 0 | 2 | 74.1 | Page | 3 |  | 1.3 | 49.4
|  | Diseño de alto nivel | 1 | 0 | 2 | 1 | 0 | 0 | 3 | 77.1 | Page | 2 |  | 2 | 51.4
|  | Plan de pruebas de integración | 2 | 1 | 0 | 0.5 | 0 | 0 | 1.5 | 78.6 | Page | 1 |  | 1 | 52.4
|  | Inspección de diseño de alto nivel | 1 | 2 | 0 | 0 | 1 | 0 | 3 | 81.6 | Page | 0.7 |  | 2 | 54.4
|  | Inspección de requerimientos | 1 | 2 | 0.5 | 2 | 0.5 | 0.5 | 5.5 | 87.1 | Page | 0.7 |  | 3.7 | 58.1
IMP1 |  | Planeación de implementación | 2 | 1 | 1 | 0 | 0 | 1 | 3 | 90.1 | Page | 1 |  | 2 | 60.1
|  | Diseño detallado | 1 | 0 | 0 | 2 | 0 | 0 | 2 | 92.1 | Page | 3 |  | 1.3 | 61.4
|  | Revisión de diseño detallado | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 93.1 |  |  |  | 0.7 | 62.1
|  | Desarrollo de pruebas | 1 | 0 | 0 | 0 | 1 | 1 | 2 | 95.1 | Page |  |  | 1.3 | 63.4
|  | Inspección detallada del diseño | 2 | 0 | 0 | 0.5 | 0 | 1 | 1.5 | 96.6 | Page | 0.7 |  | 1 | 64.4
|  | Código | 5 | 5 | 5 | 5 | 5 | 5 | 25 | 121.6 | LOC | 646 |  | 16.7 | 81.1
|  | Revisión de código | 5 | 0 | 1 | 0 | 1 | 0 | 2 | 123.6 |  |  |  | 1.3 | 82.4
|  | Inspección de código | 1 | 0 | 0 | 0 | 0.5 | 0.5 | 1 | 124.6 | Page | 0.7 |  | 0.7 | 83.1
TEST1 |  | Pruebas unitarias | 1 | 1 | 1 | 1 | 1 | 1 | 5 | 129.6 | Page | 6 |  | 3.3 | 86.4
|  | Construir e integrar el sistema | 5 | 0 | 1 | 0 | 1 | 1 | 3 | 132.6 |  |  |  | 2 | 88.4
|  | Pruebas del sistema | 2 | 0 | 1 | 0 | 2 | 2 | 5 | 137.6 | Page | 10 |  | 3.3 | 91.7
PM1 |  | Documentación | 5 | 1 | 1 | 1 | 1 | 1 | 5 | 142.6 | Page | 5 |  | 3.3 | 95
|  | Postmortem | 5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 7.5 | 150.1 | Page | 5 |  | 5 | 100
|  |  |  | 29.9 | 30.1 | 30.1 | 30.1 | 29.9 | 150.1 |  |  |  |  | 100