## Hoja1
TSPi Example Task Planning Template - Form TASK
Name |  |  |  | Date | 2014-03-21
Team | Click IT |  |  | Instructor | Luis Daniel Benavides
Part/Level |  |  |  | Cycle | 1
Task |  |  |  | Plan Hours | [6 empty] | Plan Size/Value |  |  |  |  | Actual
Phase | Part | Task Name | # Engineers | Team Leader | Development Manager | Planning Manager | Qual./Proc. Manager | Support Manager | Total Team Hours | Cumulative hours | Size Units | Size | Week No. | Planned Value | Cumulative PV | Hours | Cumulative Hours | Week No.
LAU1 |  | Definir Objetivos | 5 | 2 | 2 | 2 | 2 | 2 | 10 | 10 | Page | 2 | 1 | 6.6 | 6.6 | 10 | 10 | 1
|  | Diligenciar Info Form | 5 | 1 | 1 | 1 | 1 | 1 | 5 | 15 | Page | 5 | 1 | 3.3 | 9.9 | 5 | 15 | 1
|  | Asignar roles | 5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 2.5 | 17.5 | Page | 1 | 1 | 1.7 | 11.6 | 2.5 | 17.5 | 1
STRAT1 |  | Establecer Estrategia | 5 | 1 | 1 | 1 | 1 | 1 | 5 | 22.5 | Page | 1 | 3 | 3.3 | 14.9 | 7 | 24.5 | 3
|  | Realizar diseño Conceptual | 5 | 0.5 | 2 | 2 | 0.5 | 0.5 | 5.5 | 28 | Page | 1 | 3 | 3.7 | 18.6 | 4 | 28.5 | 3
|  | Generar acta de reunión de documentación de estrategia y criterios | 1 | 0 | 0 | 0 | 0.7 | 0 | 0.7 | 28.7 | Page | 2 | 3 | 0.5 | 19.1 | 1 | 29.5 | 3
PLAN1 |  | Realizar plan de desarrollo | 5 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 3 | 31.7 | Page | 1 | 3 | 2 | 21.1 | 2 | 31.5 | 3
|  | Realizar estimaciones preliminares de tamaño y tiempo para la estrategia | 2 | 0 | 0.5 | 1 | 0 | 0 | 1.5 | 33.2 | Page | 0.5 | 3 | 1 | 22.1 | 2 | 33.5 | 3
|  | Definir la configuracion control process | 5 | 0.2 | 0.2 | 0.2 | 0.2 | 1.5 | 2.3 | 35.5 | Page | 1 | 3 | 1.5 | 23.6 | 2 | 35.5 | 3
|  | Generar listado de tareas del ciclo | 5 | 0.5 | 0.5 | 1 | 0.5 | 0.5 | 3 | 38.5 | Page | 1 | 3 | 2 | 25.6 | 3 | 38.5 | 3
|  | Realizar plan de calidad(Definir estándares) | 5 | 0.3 | 0.3 | 0.3 | 1 | 0.3 | 2.2 | 40.7 | Page | 3 | 3 | 1.5 | 27.1 | 3 | 41.5 | 3
|  | Generar los riesgos del proyecto | 1 | 2 | 0.2 | 0.2 | 0.2 | 0.2 | 2.8 | 43.5 | Page | 2 | 3 | 1.9 | 29 | 2 | 43.5 | 3
|  | Management and miscellaneous(reuniones) | 5 | 3 | 3 | 3 | 3 | 3 | 15 | 58.5 | Page | 5 | 3 | 10 | 39 | 12 | 55.5 | 3
REQ1 |  | Requerimientos funcionales | 3 | 2 | 2 | 2 | 0 | 0 | 6 | 64.5 | Page | 1 | 4 | 4 | 43 | 6.9 | 62.4 | 4
|  | Interfaz de usuario | 3 | 1 | 1 | 0 | 0 | 1 | 3 | 67.5 | Page | 2 | 4 | 2 | 45 | 8.6 | 71 | 4
|  | Requerimientos de calidad | 2 | 0 | 0 | 0 | 2 | 1 | 3 | 70.5 | Page | 1 | 4 | 2 | 47 | 1 | 72 | 4
|  | Restricciones | 2 | 0 | 0 | 0 | 0.5 | 1.5 | 2 | 72.5 | Page | 1 | 4 | 1.3 | 48.3 | 2.4 | 74.4 | 4
DES1 |  | Plan de pruebas de sistema | 2 | 1 | 0 | 0 | 1 | 0 | 2 | 74.5 | Page | 3 | 4 | 1.3 | 49.6 | 5.8 | 80.2 | 4
|  | Diseño de alto nivel | 2 | 0 | 2 | 1 | 0 | 0 | 3 | 77.5 | Page | 2 | 4 | 2 | 51.6 | 3.4 | 83.6 | 4
|  | Plan de pruebas de integración | 2 | 1 | 0 | 0.5 | 0 | 0 | 1.5 | 79 | Page | 1 | 4 | 1 | 52.6 | 1.9 | 85.5 | 5
|  | Inspección de diseño de alto nivel | 2 | 2 | 0 | 0 | 1 | 0 | 3 | 82 | Page | 0.7 | 4 | 2 | 54.6 | 3.3 | 88.8 | 5
|  | Inspección de requerimientos | 5 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 3 | 85 | Page | 0.7 | 4 | 2 | 56.6 | 3.3 | 92.1 | 4
IMP1 |  | Planeación de implementación | 2 | 1 | 1 | 0 | 0 | 1 | 3 | 88 | Page | 1 | 5 | 2 | 58.6 | 5.8 | 97.9 | 5
|  | Diseño detallado | 1 | 0 | 0 | 3.5 | 0 | 0 | 3.5 | 91.5 | Page | 3 | 5 | 2.3 | 60.9 | 4.5 | 102.4 | 5
|  | Revisión de diseño detallado | 1 | 1 | 0 | 1 | 0 | 0 | 2 | 93.5 |  |  | 5 | 1.3 | 62.2 | 2.7 | 105.1 | 5
|  | Desarrollo de pruebas | 1 | 0 | 0 | 0 | 1 | 1 | 2 | 95.5 | Page |  | 5 | 1.3 | 63.5 | 4 | 109.1 | 5
|  | Inspección detallada de pruebas | 2 | 0 | 0 | 0.5 | 0 | 1 | 1.5 | 97 | Page | 0.7 | 5 | 1 | 64.5 | 1 | 110.1 | 5
|  | Código | 5 | 5 | 5 | 5 | 5 | 5 | 25 | 122 | LOC | 310 | 5 | 16.6 | 81.1 | 27.6 | 137.7 | 5
|  | Revisión de código | 5 | 0 | 1 | 0 | 1 | 0 | 2 | 124 |  |  | 5 | 1.3 | 82.4 | 4.9 | 142.6 | 5
|  | Inspección de código | 1 | 0 | 0 | 0 | 0.5 | 0.5 | 1 | 125 | Page | 0.7 | 5 | 0.7 | 83.1 | 4 | 146.6 | 5
TEST1 |  | Pruebas unitarias | 1 | 1 | 1 | 1 | 1 | 1 | 5 | 130 | Page | 6 | 5 | 3.3 | 86.4 | 6.9 | 153.5 | 6
|  | Construir e integrar el sistema | 5 | 0 | 1 | 0 | 1 | 1 | 3 | 133 |  |  | 5 | 2 | 88.4 | 4.7 | 158.2 | 6
|  | Pruebas del sistema | 2 | 0 | 1 | 0 | 2 | 2 | 5 | 138 | Page | 10 | 5 | 3.3 | 91.7 | 7 | 165.2 | 6
PM1 |  | Documentación | 5 | 1 | 1 | 1 | 1 | 1 | 5 | 143 | Page | 5 | 6 | 3.3 | 95 | 9.6 | 174.8 | 6
|  | Postmortem | 5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 7.5 | 150.5 | Page | 5 | 6 | 5 | 100 | 12.2 | 187 | 6
|  |  |  | 30 | 30.2 | 30.2 | 30.1 | 30 | 150.5 |  |  |  |  | 100 |  | 187
CICLO 2
Task |  |  |  | Plan Hours | [6 empty] | Plan Size/Value |  |  |  |  | Actual
Phase | Part | Task Name | # Engineers | Team Leader | Development Manager | Planning Manager | Qual./Proc. Manager | Support Manager | Total Team Hours | Cumulative hours | Size Units | Size | Week No. | Planned Value | Cumulative PV | Hours | Cumulative Hours | Week No.
LAU2 |  | Lanzamiento ciclo2 | 5 | 0,3 | 0,3 | 0,3 | 0,3 | 0,3 | 1.5 | 1.5 | Page | 18 | 6 | 1.1 | 1.1 | 0 | 0 | 7
STRAT2 |  | Verificar Estrategia | 5 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 1.5 | 3 | Page | 1 | 6 | 1.1 | 2.2 | 0 | #¡REF! | 7
|  | Realizar diseño Conceptual | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 4 | Page | 2 | 6 | 0.7 | 2.9 | 0 | #¡REF! | 7
PLAN2 |  | Actualizar estimaciones preliminares de tamaño y tiempo para la estrategia | 5 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 1 | 5 | Page | 0,5 | 6 | 0.7 | 3.6 | 0 | #¡REF! | 7
|  | Generar listado de tareas del ciclo | 5 | 0.5 | 0.5 | 1 | 0.5 | 0.5 | 3 | 8 | Page | 1 | 6 | 2.2 | 5.8 | 0 | #¡REF! | 7
|  | revisi | 1 | 0 | 0 | 0 | 1.5 | 0 | 1.5 | 9.5 | Page | 8 | 6 | 1.1 | 6.9 | 0 | #¡REF! | 7
|  | Diligenciar SUMS - Planeado | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 10.5 | Page | 1 | 6 | 0.7 | 7.6 |  |  | 7
|  | Diligenciar SUMP | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 11.5 | Page | 2 | 6 | 0.7 | 8.3 |  |  | 7
|  | Generar los riesgos del proyecto (ITL) | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 12.5 | Page | 2 | 6 | 0.7 | 9 | 0 | #¡REF! | 7
REQ2 |  | Requerimientos funcionales | 1 | 0 | 0 | 0 | 0 | 2 | 2 | 14.5 | Page | 2 | 7 | 1.5 | 10.5 | 0 | #¡REF! | 7
|  | Interfaz de usuario | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 15.5 | Page | 1 | 7 | 0.7 | 11.2 | 0 | #¡REF! | 7
|  | Requerimientos de calidad | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 16.5 | Page | 1 | 7 | 0.7 | 11.9 | 0 | #¡REF! | 7
DES2 |  | Plan de pruebas de sistema | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 18.5 | Page | 3 | 7 | 1.5 | 13.4 | 0 | #¡REF! | 7
|  | Diseño de alto nivel | 1 | 2 | 0 | 0 | 0 | 0 | 2 | 20.5 | Page | 2 | 7 | 1.5 | 14.9 | 0 | #¡REF! | 7
|  | Plan de pruebas de integración | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 21.5 | Page | 1 | 7 | 0.7 | 15.6 | 0 | #¡REF! | 7
|  | Inspección de diseño de alto nivel | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 22.5 | Page | 0,7 | 7 | 0.7 | 16.3 | 0 | #¡REF! | 7
|  | Inspección de requerimientos | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 23.5 | Page | 0,7 | 7 | 0.7 | 17 | 0 | #¡REF! | 7
|  | Reunion semana 7 | 5 | 1 | 1 | 1 | 1 | 1 | 5 | 28.5 |  |  | 7 | 3.7 | 20.7 |  |  | 7
|  | Acta de reunión semana 7 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 29.5 | Page | 2 | 7 | 0.7 | 21.4 |  |  | 7
|  | Diligenciamiento de week, task, schedule, logT personales | 5 | 2 | 2 | 2 | 2 | 2 | 10 | 39.5 | Page | 20 | 7 | 7.4 | 28.8
|  | Diligenciamiento de task de equipo | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 40.5 | page | 1 | 7 | 0.7 | 29.5
|  | Diligenciamiento de schedule de equipo | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 41.5 | page | 1 | 7 | 0.7 | 30.2
|  | Diligenciamiento de week de equipo | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 42.5 | page | 1 | 7 | 0.7 | 30.9
IMP2 |  | Diseño detallado | 1 | 0 | 0 | 0 | 0 | 2 | 2 | 44.5 | Page | 3 | 8 | 1.5 | 32.4 | 0 | #¡REF!
|  | Revisión de diseño detallado | 1 | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 45 |  |  | 8 | 0.4 | 32.8 | 0 | #¡REF!
|  | Inspección de diseño detallado | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 45.5 | page | 1 | 8 | 0.4 | 33.2
|  | Documentación de pruebas unitarias | 1 | 0 | 0 | 2 | 0 | 0 | 2 | 47.5 | Page | 2 | 8 | 1.5 | 34.7 | 0 | #¡REF!
|  | Código | 5 | 3 | 9 | 3 | 3 | 3 | 21 | 68.5 | LOC | 336 | 8 | 15.6 | 50.3 | 0 | #¡REF!
|  | Revisión de código | 1 | 0 | 0 | 0 | 0 | 3 | 3 | 71.5 |  |  | 8 | 2.2 | 52.5 | 0 | #¡REF!
|  | Inspección de código | 1 | 3 | 0 | 0 | 0 | 0 | 3 | 74.5 | Page | 1 | 8 | 2.2 | 54.7 | 0 | #¡REF!
TEST2 |  | Desarrollo de pruebas unitarias JUNIT | 1 | 0 | 0 | 2 | 0 | 0 | 2 | 76.5 | LOC | 100 | 8 | 1.5 | 56.2 | 0 | #¡REF!
TEST2 |  | Construir e integrar el sistema | 5 | 1 | 1 | 1 | 1 | 1 | 5 | 81.5 | page | 2 | 8 | 3.7 | 59.9 | 0 | #¡REF!
|  | Pruebas del sistema | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 83.5 | Page | 10 | 8 | 1.5 | 61.4 | 0 | #¡REF!
|  | Ejecución Pruebas unitarias JUNIT y actualización errores | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 84.5 | page | 1 | 8 | 0.7 | 62.1
|  | Reunion semana 8 | 5 | 1 | 1 | 1 | 1 | 1 | 5 | 89.5 | page | 1 | 8 | 3.7 | 65.8
|  | Acta de reunión semana 8 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 90.5 | page | 1 | 8 | 0.7 | 66.5
|  | Diligenciamiento de week, task, schedule, logT personales | 5 | 2 | 2 | 2 | 2 | 2 | 10 | 100.5 | page | 20 | 8 | 7.4 | 73.9
|  | Diligenciamiento de task de equipo | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 101.5 | page | 1 | 8 | 0.7 | 74.6
|  | Diligenciamiento de schedule de equipo | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 102.5 | page | 1 | 8 | 0.7 | 75.3
|  | Diligenciamiento de week de equipo | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 103.5 | page | 1 | 8 | 0.7 | 76
PM2 |  | Documentación-Actualizar SUMQ | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 105.5 | Page | 5 | 9 | 1.5 | 77.5 | 0 | #¡REF!
|  | Diligenciar SUMS - Actual | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 106.5 | page | 1 | 9 | 0.7 | 78.2
|  | Documentación-Actualizar SUMP | 1 | 1.5 | 0 | 0 | 0 | 0 | 1.5 | 108 | page | 2 | 9 | 1.1 | 79.3
|  | Diligenciar PIP | 5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 2.5 | 110.5 | page | 2 | 9 | 1.9 | 81.2
|  | Diligenciar peer | 5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 2.5 | 113 | page | 5 | 9 | 1.9 | 83.1
|  | Manual de usuario | 1 | 0 | 2 | 0 | 0 | 0 | 2 | 115 | page | 4 | 9 | 1.5 | 84.6
|  | Manual de Instalación | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 116 |  |  |  | 0.7 | 85.3
|  | Postmortem | 5 | 1 | 1 | 1 | 1 | 1 | 5 | 121 | Page | 5 | 9 | 3.7 | 89 | 0 | #¡REF!
|  | Acta de reunión semana 9 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 122 | page | 2 | 9 | 0.7 | 89.7
|  | Diligenciamiento de week, task, schedule, logT personales | 5 | 2 | 2 | 2 | 2 | 2 | 10 | 132 | page | 20 | 9 | 7.4 | 97.1
|  | Diligenciamiento de task de equipo | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 133 | page | 1 | 9 | 0.7 | 97.8
|  | Diligenciamiento de schedule de equipo | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 134 | page | 1 | 9 | 0.7 | 98.5
|  | Diligenciamiento de week de equipo | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 135 | page | 1 | 9 | 0.7 | 99.2
|  |  |  | 27 | 26 | 26.5 | 27 | 27 | 135 |  |  |  |  | 99.2 |  | 0