## Hoja1
TSPi Schedule Planning Template - Form SCHEDULE
Name |  | Fabián Eduardo Becerra Pérez |  |  |  |  | Date |  | 2014-04-16
Team |  | Click IT |  |  |  |  | Instructor |  | Luis Daniel Benavides
Part/Level | [6 empty] | Cycle |  | 2
|  |  | Plan |  |  | Actual
Week No | Date |  | Direct Hours | Cumulative Hours | Cumulative Planned Value | Team Hours |  | Cumulative Hours | Week Earned Value | Cumulative Earned Value
6 | 16/04/214 |  | 4.3 | 4.3 | 14.9 | 0 |  | 0 | 0 | 0
7 | 2014-04-23 |  | 3 | 7.3 | 25.3 | 8.62 |  | 8.62 | 25.3 | 25.3
8 | 2014-04-30 |  | 14.5 | 21.8 | 75.6 | 15.5 |  | 24.12 | 50.3 | 75.6
9 | 2014-05-07 |  | 7 | 28.8 | 100