## Hoja1
TSPi Schedule Planning Template - Form SCHEDULE
Name |  | Claudia Vargas |  |  |  |  | Date |  | 2014-04-23
Team |  | Click IT |  |  |  |  | Instructor |  | Luis Daniel Benavides
Part/Level | [6 empty] | Cycle |  | 2
|  |  | Plan |  |  | Actual
Week No | Date |  | Direct Hours | Cumulative Hours | Cumulative Planned Value | Hours |  | Cumulative Hours | Week Earned Value | Cumulative Earned Value
6 | 16/04/214 |  | 2.8 | 2.8 | 10.3 | 0 |  | 0 | 0 | 0
7 | 2014-04-23 |  | 7 | 9.8 | 25.6 | 11.7 |  | 11.7 | 35.9 | 35.9
8 | 2014-04-30 |  | 10.5 | 20.3 | 38.5 | 12.5 |  | 24.2 | 38.5 | 74.4
9 | 2014-05-07 |  | 7 | 27.3 | 25.6 | 7.9 |  | 32.1 | 25.6 | 100
|  |  | 27.3 |  |  | 32.1