## Hoja1
TSPi Schedule Planning Template - Form SCHEDULE
Name |  | Claudia Vargas |  |  |  |  | Date |  | 2014-04-23
Team |  | Click IT |  |  |  |  | Instructor |  | Luis Daniel Benavides
Part/Level | [6 empty] | Cycle |  | 2
|  |  | Plan |  |  | Actual
Week No | Date |  | Direct Hours | Cumulative Hours | Cumulative Planned Value | Hours |  | Cumulative Hours | Week Earned Value | Cumulative Earned Value
6 | 16/04/214 |  | 2 | 2 | 8.5 | 0 |  | 0 | 0 | 0
7 | 2014-04-23 |  | 7 | 9 | 34.4 | 9.62 |  | 9.62 | 34.4 | 34.4
8 | 2014-04-30 |  | 13 | 22 | 82.5 | 8 |  | 17.62 | 48.1 | 82.5
9 | 2014-05-07 |  |  |  | 0
|  |  | 22 |  |  | 17.62 |  |  | 82.5