## Hoja1
TSPi Schedule Planning Template - Form SCHEDULE
Name | [6 empty] | Date |  | 2014-04-30
Team |  | Click IT |  |  |  |  | Instructor |  | Luis Daniel Benavides
Part/Level | [6 empty] | Cycle |  | 2
ciclo 2
|  |  | Plan |  |  | Actual
Week No | Date |  | Direct Hours | Cumulative Hours | Cumulative Planned Value | Team Hours |  | Cumulative Hours | Week Earned Value | Cumulative Earned Value
6 | 2014-04-16 |  | 12 | 12 | 8.2 | 0 |  | 0 | 0 | 0
7 | 2014-04-23 |  | 30 | 42 | 20.8 | 50.9 |  | 50.9 | 29 | 29
8 | 2014-04-30 |  | 66.5 | 108.5 | 45.8 | 76.1 |  | 127 | 45.8 | 74.8
9 | 2014-05-07 |  | 36.5 | 145 | 25.1
[6 empty] | 127 |  |  | 74.8