## Hoja1
TSPi Example Task Planning Template - Form TASK
Name | Rafael Andrés Ortega Pabón |  |  | Date | 2014-03-20
Team | Click IT |  |  | Instructor | Luis Daniel Benavides
Part/Level | 1 |  |  | Cycle | 1
Task |  |  | Plan Hours |  | Plan Size/Value |  |  |  |  | Actual
Phase | Part | Task Name | Team Leader | Cumulative hours | Size Units | Size | Week No. | Planned Value | Cumulative PV | Hours | Cumulative Hours | Week No.
LAU1 |  | Definir Objetivos | 2 | 2 | Page | 2 | 1 | 6.7 | 6.7 | 1.9 | 1.9 | 1
|  | Diligenciar Info Form | 1 | 3 | Page | 5 | 1 | 3.3 | 10 | 1 | 2.9 | 1
|  | Asignar roles | 0.5 | 3.5 | Page | 1 | 1 | 1.7 | 11.7 | 0.4 | 3.3 | 1
STRAT1 |  | Establecer Estrategia | 1 | 4.5 | Page | 1 | 3 | 3.3 | 15 | 1.5 | 4.8 | 3
|  | Realizar diseño Conceptual | 0.5 | 5 | Page | 1 | 3 | 1.7 | 16.7 | 1 | 5.8 | 3
PLAN1 |  | Realizar plan de desarrollo | 0.5 | 5.5 | Page | 1 | 3 | 1.7 | 18.4 | 0.5 | 6.3 | 3
|  | Definir la configuracion control process | 0.2 | 5.7 | Page | 1 | 3 | 0.7 | 19.1 | 0.2 | 6.5 | 3
|  | Generar listado de tareas de la semana | 0.5 | 6.2 | Page | 1 | 3 | 1.7 | 20.8 | 0.6 | 7.1 | 3
|  | Realizar plan de calidad(Definir estándares) | 0.3 | 6.5 | Page | 3 | 3 | 1 | 21.8 | 0.5 | 7.6 | 3
|  | Generar los riesgos del proyecto | 2 | 8.5 | Page | 2 | 3 | 6.7 | 28.5 | 1.9 | 9.5 | 3
|  | Management and miscellaneous(reuniones) | 3 | 11.5 | Page | 5 | 3 | 10 | 38.5 | 3 | 12.5 | 3
REQ1 |  | Requerimientos funcionales | 2 | 13.5 | Page | 1 | 4 | 6.7 | 45.2 | 2.5 | 15 | 4
|  | Interfaz de usuario | 1 | 14.5 | Page | 2 | 4 | 3.3 | 48.5 | 3 | 18 | 4
DES1 |  | Plan de pruebas de sistema | 1 | 15.5 | Page | 3 | 4 | 3.3 | 51.8 | 1.8 | 19.8 | 4
|  | Plan de pruebas de integración | 1 | 16.5 | Page | 1 | 4 | 3.3 | 55.1 | 0.9 | 20.7 | 4
|  | Inspección de diseño de alto nivel | 2 | 18.5 | Page | 0.7 | 4 | 6.7 | 61.8 | 2.1 | 22.8 | 4
|  | Inspección de requerimientos | 1 | 19.5 | Page | 0.7 | 4 | 3.3 | 65.1 | 1.3 | 24.1 | 4
IMP1 |  | Planeación de implementación | 1 | 20.5 | Page | 1 | 5 | 3.3 | 68.4 | 1.8 | 25.9 | 5
|  | Revisión de diseño detallado | 1 | 21.5 |  |  | 5 | 3.3 | 71.7 | 0.7 | 26.6 | 5
|  | Código | 5 | 26.5 | LOC | 646 | 5 | 16.7 | 88.4 | 6.2 | 32.8 | 5
TEST1 |  | Pruebas unitarias | 1 | 27.5 | Page | 6 | 5 | 3.3 | 91.7 | 0.7 | 33.5 | 5
PM1 |  | Documentación | 1 | 28.5 | Page | 5 | 6 | 3.3 | 95 | 2.3 | 35.8 | 6
|  | Postmortem | 1.5 | 30 | Page | 5 | 6 | 5 | 100 | 1.8 | 37.6 | 6
30