## Hoja1
TSPi Example Task Planning Template - Form TASK
Name | Fabián Eduardo Becerra Pérez |  | Date | 2014-03-21
Team | Click IT |  | Instructor | Luis Daniel Benavides
Part/Level |  |  | Cycle | 1
Task |  |  | Plan Hours |  | Plan Size/Value |  |  |  |  | Actual
Phase | Part | Task Name | Planning Manager | Cumulative hours | Size Units | Size | Week No. | Planned Value | Cumulative PV | Hours | Cumulative Hours | Week No.
LAU1 |  | Definir Objetivos | 2 | 2 | Page | 2 | 1 | 6.6 | 6.6 | 2 | 2 | 1
|  | Diligenciar Info Form | 1 | 3 | Page | 5 | 1 | 3.3 | 9.9 | 1 | 3 | 1
|  | Asignar roles | 0.5 | 3.5 | Page | 1 | 1 | 1.7 | 11.6 | 0.5 | 3.5 | 1
STRAT1 |  | Establecer Estrategia | 1 | 4.5 | Page | 1 | 3 | 3.3 | 14.9 | 1.4 | 4.9 | 3
|  | Realizar diseño Conceptual | 2 | 6.5 | Page | 1 | 3 | 6.6 | 21.5 | 1.5 | 6.4 | 3
PLAN1 |  | Realizar plan de desarrollo | 0.5 | 7 | Page | 1 | 3 | 1.7 | 23.2 | 0.3 | 6.7 | 3
|  | Realizar estimaciones preliminares de tamaño y tiempo para la estrategia | 1 | 8 | Page | 1 | 3 | 3.3 | 26.5 | 1.3 | 8 | 3
|  | Definir la configuracion control process | 0.2 | 8.2 | Page | 1 | 3 | 0.7 | 27.2 | 0.2 | 8.2 | 3
|  | Generar listado de tareas del ciclo | 1 | 9.2 | Page | 1 | 3 | 3.3 | 30.5 | 1 | 9.2 | 3
|  | Realizar plan de calidad(Definir estándares) | 0.3 | 9.5 | Page | 3 | 3 | 1 | 31.5 | 0.4 | 9.6 | 3
|  | Generar los riesgos del proyecto | 0.2 | 9.7 | Page | 2 | 3 | 0.7 | 32.2 | 0.1 | 9.7 | 3
|  | Management and miscellaneous(reuniones) | 3 | 12.7 | Page | 5 | 3 | 9.9 | 42.1 | 2.4 | 12.1 | 3
REQ1 |  | Requerimientos funcionales | 2 | 14.7 | Page | 1 | 4 | 6.6 | 48.7 | 3 | 15.1 | 4
DES1 |  | Diseño de alto nivel | 1 | 15.7 | Page | 2 | 4 | 3.3 | 52 | 2.5 | 17.6 | 4
|  | Plan de pruebas de integración | 0.5 | 16.2 | Page | 1 | 4 | 1.7 | 53.7
|  | Inspección de requerimientos | 0.5 | 16.7 | Page | 0.7 | 4 | 1.7 | 55.4
IMP1 |  | Diseño detallado | 3.5 | 20.2 | Page | 3 | 5 | 11.6 | 67
|  | Revisión de diseño detallado | 1 | 21.2 |  |  | 5 | 3.3 | 70.3
|  | Inspección detallada de pruebas | 0.5 | 21.7 | Page | 0.7 | 5 | 1.7 | 72
|  | Código | 5 | 26.7 | LOC | 646 | 5 | 16.6 | 88.6
TEST1 |  | Pruebas unitarias | 1 | 27.7 | Page | 10 | 5 | 3.3 | 91.9
PM1 |  | Documentación | 1 | 28.7 | Page | 5 | 6 | 3.3 | 95.2
|  | Postmortem | 1.5 | 30.2 | Page | 5 | 6 | 5 | 100
30.2