## Hoja1
TSPi Schedule Planning Template - Form SCHEDULE
Name |  | Claudia Vargas |  |  |  |  | Date |  | 2014-03-21
Team |  | Click IT |  |  |  |  | Instructor |  | Luis Daniel Benavides
Part/Level | [6 empty] | Cycle |  | 1
|  |  | Plan |  |  | Actual
Week No | Date |  | Direct Hours | Cumulative Hours | Cumulative Planned Value | Hours |  | Cumulative Hours | Week Earned Value | Cumulative Earned Value
1 | 12/03/214 |  | 4 | 3.5 | 12.9032 | 4 |  | 4
2 | 2014-03-20 |  | 0 | 3.5 | 12.9032 | 0 |  | 4
3 | 2014-03-24 |  | 5 | 8.5 | 29.0323 | 6.5 |  | 10.5
4 | 2014-04-02 |  | 6 | 14.5 | 48.3871
5 | 2014-02-09 |  | 10 | 24.5 | 80.6452
6 | 2014-02-16 |  | 6 | 30.5 | 100
31