## Hoja1
TSPi Example Task Planning Template - Form TASK
Name |  |  |  | Date | 2014-03-21
Team | Click IT |  |  | Instructor | Luis Daniel Benavides
Part/Level |  |  |  | Cycle | 1
Task |  |  |  | Plan Hours | [6 empty] | Plan Size/Value |  |  |  |  | Actual
Phase | Part | Task Name | # Engineers | Team Leader | Development Manager | Planning Manager | Qual./Proc. Manager | Support Manager | Total Team Hours | Cumulative hours | Size Units | Size | Week No. | Planned Value | Cumulative PV | Hours | Cumulative Hours | Week No.
LAU1 |  | Definir Objetivos | 5 | 2 | 2 | 2 | 2 | 2 | 10 | 10 | Page | 2 | 1 | 6.6 | 6.6 | 10 | 10 | 1
|  | Diligenciar Info Form | 5 | 1 | 1 | 1 | 1 | 1 | 5 | 15 | Page | 5 | 1 | 3.3 | 9.9 | 5 | 15 | 1
|  | Asignar roles | 5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 2.5 | 17.5 | Page | 1 | 1 | 1.7 | 11.6 | 2.5 | 17.5 | 1
STRAT1 |  | Establecer Estrategia | 5 | 1 | 1 | 1 | 1 | 1 | 5 | 22.5 | Page | 1 | 3 | 3.3 | 14.9 | 7 | 24.5 | 3
|  | Realizar diseño Conceptual | 5 | 0.5 | 2 | 2 | 0.5 | 0.5 | 5.5 | 28 | Page | 1 | 3 | 3.7 | 18.6 | 4 | 28.5 | 3
|  | Generar acta de reunión de documentación de estrategia y criterios | 1 | 0 | 0 | 0 | 0.7 | 0 | 0.7 | 28.7 | Page | 2 | 3 | 0.5 | 19.1 | 1 | 29.5 | 3
PLAN1 |  | Realizar plan de desarrollo | 5 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 3 | 31.7 | Page | 1 | 3 | 2 | 21.1 | 2 | 31.5 | 3
|  | Realizar estimaciones preliminares de tamaño y tiempo para la estrategia | 2 | 0 | 0.5 | 1 | 0 | 0 | 1.5 | 33.2 | Page | 0.5 | 3 | 1 | 22.1 | 2 | 33.5 | 3
|  | Definir la configuracion control process | 5 | 0.2 | 0.2 | 0.2 | 0.2 | 1.5 | 2.3 | 35.5 | Page | 1 | 3 | 1.5 | 23.6 | 2 | 35.5 | 3
|  | Generar listado de tareas del ciclo | 5 | 0.5 | 0.5 | 1 | 0.5 | 0.5 | 3 | 38.5 | Page | 1 | 3 | 2 | 25.6 | 3 | 38.5 | 3
|  | Realizar plan de calidad(Definir estándares) | 5 | 0.3 | 0.3 | 0.3 | 1 | 0.3 | 2.2 | 40.7 | Page | 3 | 3 | 1.5 | 27.1 | 3 | 41.5 | 3
|  | Generar los riesgos del proyecto | 1 | 2 | 0.2 | 0.2 | 0.2 | 0.2 | 2.8 | 43.5 | Page | 2 | 3 | 1.9 | 29 | 2 | 43.5 | 3
|  | Management and miscellaneous(reuniones) | 5 | 3 | 3 | 3 | 3 | 3 | 15 | 58.5 | Page | 5 | 3 | 10 | 39 | 5 | 48.5 | 3
REQ1 |  | Requerimientos funcionales | 3 | 2 | 2 | 2 | 0 | 0 | 6 | 64.5 | Page | 1 |  | 4 | 43
|  | Interfaz de usuario | 3 | 1 | 1 | 0 | 0 | 1 | 3 | 67.5 | Page | 2 |  | 2 | 45
|  | Requerimientos de calidad | 2 | 0 | 0 | 0 | 2 | 1 | 3 | 70.5 | Page | 1 |  | 2 | 47
|  | Restricciones | 2 | 0 | 0 | 0 | 0.5 | 1.5 | 2 | 72.5 | Page | 1 |  | 1.3 | 48.3
DES1 |  | Plan de pruebas de sistema | 2 | 1 | 0 | 0 | 1 | 0 | 2 | 74.5 | Page | 3 |  | 1.3 | 49.6
|  | Diseño de alto nivel | 2 | 0 | 2 | 1 | 0 | 0 | 3 | 77.5 | Page | 2 |  | 2 | 51.6
|  | Plan de pruebas de integración | 2 | 1 | 0 | 0.5 | 0 | 0 | 1.5 | 79 | Page | 1 |  | 1 | 52.6
|  | Inspección de diseño de alto nivel | 2 | 2 | 0 | 0 | 1 | 0 | 3 | 82 | Page | 0.7 |  | 2 | 54.6
|  | Inspección de requerimientos | 5 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 3 | 85 | Page | 0.7 |  | 2 | 56.6
IMP1 |  | Planeación de implementación | 2 | 1 | 1 | 0 | 0 | 1 | 3 | 88 | Page | 1 |  | 2 | 58.6
|  | Diseño detallado | 1 | 0 | 0 | 3.5 | 0 | 0 | 3.5 | 91.5 | Page | 3 |  | 2.3 | 60.9
|  | Revisión de diseño detallado | 1 | 1 | 0 | 1 | 0 | 0 | 2 | 93.5 |  |  |  | 1.3 | 62.2
|  | Desarrollo de pruebas | 1 | 0 | 0 | 0 | 1 | 1 | 2 | 95.5 | Page |  |  | 1.3 | 63.5
|  | Inspección detallada de pruebas | 2 | 0 | 0 | 0.5 | 0 | 1 | 1.5 | 97 | Page | 0.7 |  | 1 | 64.5
|  | Código | 5 | 5 | 5 | 5 | 5 | 5 | 25 | 122 | LOC | 646 |  | 16.6 | 81.1
|  | Revisión de código | 5 | 0 | 1 | 0 | 1 | 0 | 2 | 124 |  |  |  | 1.3 | 82.4
|  | Inspección de código | 1 | 0 | 0 | 0 | 0.5 | 0.5 | 1 | 125 | Page | 0.7 |  | 0.7 | 83.1
TEST1 |  | Pruebas unitarias | 1 | 1 | 1 | 1 | 1 | 1 | 5 | 130 | Page | 6 |  | 3.3 | 86.4
|  | Construir e integrar el sistema | 5 | 0 | 1 | 0 | 1 | 1 | 3 | 133 |  |  |  | 2 | 88.4
|  | Pruebas del sistema | 2 | 0 | 1 | 0 | 2 | 2 | 5 | 138 | Page | 10 |  | 3.3 | 91.7
PM1 |  | Documentación | 5 | 1 | 1 | 1 | 1 | 1 | 5 | 143 | Page | 5 |  | 3.3 | 95
|  | Postmortem | 5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 7.5 | 150.5 | Page | 5 |  | 5 | 100
|  |  |  | 30 | 30.2 | 30.2 | 30.1 | 30 | 150.5 |  |  |  |  | 100