## Hoja1
TSPi Schedule Development Template - Form SCHEDULE
Name |  | Layne Granados Mogollón |  |  |  |  | Date |  | 2014-03-21
Team |  | Click IT |  |  |  |  | Instructor |  | Luis Daniel Benavides
Part/Level | [6 empty] | Cycle |  | 1
|  |  | Plan |  |  | Actual
Week No | Date |  | Direct Hours | Cumulative Hours | Cumulative Planned Value | Hours |  | Cumulative Hours | Week Earned Value | Cumulative Earned Value
1 | 12/03/214 |  | 3.5 | 3.5 | 11.5894 | 3.5 |  | 3.5 | 11.6 | 11.6
2 | 2014-03-19 |  | 0 | 3.5 | 11.5894 | 0 |  | 3.5 | 0 | 11.6
3 | 2014-03-26 |  | 8.7 | 12.2 | 40.3974 | 8.14 |  | 11.64 | 28.9 | 40.5
4 | 2014-04-02 |  | 5.5 | 17.7 | 58.6093 | 7.6 |  | 19.24 | 18.2 | 58.7
5 | 2014-02-09 |  | 10 | 27.7 | 91.7219 | 30.1 |  | 49.34 | 23.1 | 81.8
6 | 2014-02-16 |  | 2.5 | 30.2 | 100 | 10.1 |  | 59.44 | 18.2 | 100
30.2