## Hoja1
TSPi Schedule Planning Template - Form SCHEDULE
Name |  | Claudia Vargas |  |  |  |  | Date |  | 2014-04-23
Team |  | Click IT |  |  |  |  | Instructor |  | Luis Daniel Benavides
Part/Level | [6 empty] | Cycle |  | 2
|  |  | Plan |  |  | Actual
Week No | Date |  | Direct Hours | Cumulative Hours | Cumulative Planned Value | Hours |  | Cumulative Hours | Week Earned Value | Cumulative Earned Value
6 | 16/04/214 |  | 2.8 | 2.8 | 13.8 | 0 |  | 0 | 0 | 0
7 | 2014-04-23 |  | 7 | 9.8 | 34.5 | 11.7 |  | 11.7 | 36.3 | 36.3
8 | 2014-04-30 |  | 10.5 | 20.3 | 51.7 | 9.5 |  | 21.2 | 38.9 | 75.2
9 | 2014-05-07 |  |  |  | 0
|  |  | 20.3 |  |  | 21.2 |  |  | 75.2