## Hoja1
TSPi Schedule Planning Template - Form SCHEDULE
Name |  | Claudia Vargas |  |  |  |  | Date |  | 2014-03-21
Team |  | Click IT |  |  |  |  | Instructor |  | Luis Daniel Benavides
Part/Level | [6 empty] | Cycle |  | 1
|  |  | Plan |  |  | Actual
Week No | Date |  | Direct Hours | Cumulative Hours | Cumulative Planned Value | Team Hours |  | Cumulative Hours | Week Earned Value | Cumulative Earned Value
1 | 12/03/214 |  | 3.5 | 3.5 | 11.6279 | 3.2 |  | 3.2 | 11.6 | 11.6
2 | 2014-03-19 |  | 0 | 3.5 | 11.6279 | 0 |  | 3.2 | 0 | 11.6
3 | 2014-03-26 |  | 7.6 | 11.1 | 36.8771 | 22.5 |  | 25.7 | 26.9 | 38.5
4 | 2014-04-02 |  | 5 | 16.1 | 53.4884
5 | 2014-02-09 |  | 11.5 | 27.6 | 91.6944
6 | 2014-02-16 |  | 2.5 | 30.1 | 100
30.1